## Project Schedule
Project Schedule |  | Senior Design 1
Phase: |  | Phase 1: Build 1st Generation Copter | [15 empty] | Completed
Week Number: |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | In Works
Dates: |  | 8/19-8/25 | 8/26-9/1 | 9/2-9/8 | 9/9-9/15 | 9/16-9/22 | 9/23-9/29 | 9/30-10/6 | 10/7-10/13 | 10/14-10/20 | 10/21-10/27 | 10/28-11/3 | 11/4-11/10 | 11/11-11/17 | 11/18-11/24 | 11/25-12/1 | 12/2-12/8 | Behind
Research and Design I | [17 empty] | Future Planned | bar: Phase 1: Build 1st Generation Copter 1 to Phase 1: Build 1st Generation Copter 9
Team Formation and Organization | bar: Phase 1: Build 1st Generation Copter 1 to Phase 1: Build 1st Generation Copter 3
Software Design | bar: Phase 1: Build 1st Generation Copter 3 to Phase 1: Build 1st Generation Copter 9
Hardware Design | bar: Phase 1: Build 1st Generation Copter 3 to Phase 1: Build 1st Generation Copter 9
1st Round Parts Acquisition | bar: Phase 1: Build 1st Generation Copter 5 to Phase 1: Build 1st Generation Copter 8
Software & Hardware Implementation 1 | bar: Phase 1: Build 1st Generation Copter 9 to Phase 1: Build 1st Generation Copter 15
RTOS, Peripheral Drivers, and Control Algorithm | bar: Phase 1: Build 1st Generation Copter 9 to Phase 1: Build 1st Generation Copter 15
2nd Round Parts Acquisition | bar: Phase 1: Build 1st Generation Copter 11 to Phase 1: Build 1st Generation Copter 14
Assemble Frame, Mount Motors and Electronics | bar: Phase 1: Build 1st Generation Copter 11 to Phase 1: Build 1st Generation Copter 14
Hardware and Software Integration & Testing 1 | bar: Phase 1: Build 1st Generation Copter 12 to Phase 1: Build 1st Generation Copter 16
Use Microcontroller to Drive Motors & Read input | bar: Phase 1: Build 1st Generation Copter 12 to Phase 1: Build 1st Generation Copter 15
Assembly and Tethered Testing Copter | bar: Phase 1: Build 1st Generation Copter 13 to Phase 1: Build 1st Generation Copter 14
1st Generation Copter Testing | bar: Phase 1: Build 1st Generation Copter 16
Project Schedule |  | Phase 1: Build 1st Generation Copter 1: Senior Design 2
Phase: |  | Phase 1: Build 1st Generation Copter 1: Phase 2: Build 2nd Generation Copter; Phase 1: Build 1st Generation Copter 7: Phase 3: Replicate Copter and Testing
Week Number: |  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Dates: |  | 1/6-1/12 | 1/13-1/19 | 1/20-1/26 | 1/27-2/2 | 2/3-2/9 | 2/10-2/16 | 2/17-2/23 | 2/24-3/2 | 3/3-3/9 | 3/10-3/16 | 3/17-3/23 | 3/24-3/30 | 3/31-4/6 | 4/7-4/13 | 4/14-4/20 | 4/21-4/27
Research and Design II | bar: Phase 2: Build 2nd Generation Copter 17 to Phase 2: Build 2nd Generation Copter 20
Design PCB | bar: Phase 2: Build 2nd Generation Copter 17 to Phase 2: Build 2nd Generation Copter 20
Ground Station Software Research | bar: Phase 2: Build 2nd Generation Copter 17 to Phase 2: Build 2nd Generation Copter 20
Navigation Computer Software Design | bar: Phase 2: Build 2nd Generation Copter 17 to Phase 2: Build 2nd Generation Copter 20
Software & Hardware Implementation 2 | bar: Phase 2: Build 2nd Generation Copter 20 to Phase 3: Replicate Copter and Testing 26
Ground Station Software Implementation | bar: Phase 2: Build 2nd Generation Copter 20 to Phase 3: Replicate Copter and Testing 25
Navigation Computer Software Implementation | bar: Phase 2: Build 2nd Generation Copter 21 to Phase 3: Replicate Copter and Testing 24
Fabricate PCB | bar: Phase 2: Build 2nd Generation Copter 20 to Phase 2: Build 2nd Generation Copter 22
Mount PCB & Navigation Computer | bar: Phase 3: Replicate Copter and Testing 25 to Phase 3: Replicate Copter and Testing 26
2nd Generation Copter Feature Testing | bar: Phase 3: Replicate Copter and Testing 26 to Phase 3: Replicate Copter and Testing 28
Replicate Copter and Testing | bar: Phase 3: Replicate Copter and Testing 26 to Phase 3: Replicate Copter and Testing 32
Copter Integration | bar: Phase 3: Replicate Copter and Testing 26 to Phase 3: Replicate Copter and Testing 28
Dual Copter Testing | bar: Phase 3: Replicate Copter and Testing 29 to Phase 3: Replicate Copter and Testing 30
Buffer Time | bar: Phase 3: Replicate Copter and Testing 31 to Phase 3: Replicate Copter and Testing 32

## Budget&Parts-Detailed
Category | Item | Part # | QTY | Price Ea. ($) | Total $ | Website | Need By Date | Status
Quad:FltContlSys
… | Tiva C Launchpad | TM4C123G | 2 | 12.99 | 25.98 | http://www.ti.com/tool/ek-tm4c123gxl | 2013-09-30 | Acquired
… | 10 DoF IMU Sensor | Misc | 1 | 25.9 | 25.9 | https://www.sparkfun.com/products/10724 | 2013-09-30 | Acquired
… | 50 Channel GPS Reciever | GP-635T | 2 | 39.95 | 79.9 | https://www.sparkfun.com/products/11571 | 2013-09-30 | Acquired
Quad:FltSys
… | Electronic Speed Controller | 9192000131-0 | 8 | 12.49 | 99.92 | http://www.hobbyking.com/hobbyking/store/__43709__Afro_ESC_20Amp_Multi_rotor_Motor_Speed_Controller_SimonK_Firmware_.html | 2013-11-04 | Acquired
… | Prop Drive 900kv/270W Motors | NTM2830S-900 | 8 | 14.99 | 119.92 | http://www.hobbyking.com/hobbyking/store/__25081__NTM_Prop_Drive_Series_28_30S_900kv_270w_short_shaft_version_.html | 2013-11-04 | Acquired
… | 8x4.5 Propellers | 17000055 | 12 | 3.53 | 42.36 | http://www.hobbyking.com/hobbyking/store/__46308__8045_SF_Props_2pc_Standard_Rotation_2_pc_RH_Rotation_Red_USA_Warehouse_.html | 2013-11-04 | Acquired
… | Q450 Glass Fiber Frame (450mm) | 297000028-0 | 2 | 7.99 | 15.98 | http://www.hobbyking.com/hobbyking/store/__24172__Q450_Glass_Fiber_Quadcopter_Frame_450mm.html | 2013-11-04 | Acquired
… | 4S 5000mAh Li-Po Battery | N5000.4S.45 | 2 | 65.03 | 130.06 | http://www.hobbyking.com/hobbyking/store/__20791__Turnigy_nano_tech_5000mah_4S_45_90C_Lipo_Pack_USA_Warehouse_.html | 2013-11-04 | Acquired
| Turnigy Rx/Tx 9ch controller | TX-9X-M1 | 1 | 54 | 54 | http://www.hobbyking.com/hobbyking/store/__8991__Turnigy_9X_9Ch_Transmitter_w_Module_8ch_Receiver_Mode_1_v2_Firmware_.html | 2013-11-04 | Acquired
… | HXT 4mm to 4 X 3.5mm bullet Multistar ESC Power Breakout Cable |  | 2 | 3.65 | 7.3 | http://www.hobbyking.com/hobbyking/store/uh_viewitem.asp?idproduct=25483&aff=588847 | 2013-11-04 | Acquired
Quad:GuidSys
… | Embedded Linux Processor |  | 2 | N/A |  |  | N/A | Acquired
… | Power Cable |  | 2 | N/A |  |  | N/A | Acquired
… | SD Cards |  | 2 | N/A |  |  | N/A | Acquired
… | 802.11G Wireless Card |  | 2 | N/A |  |  | N/A | Acquired
… | RasPi 5MP Camera Board | 7757731 | 2 | 34.95 | 69.9 | http://www.amazon.com/Raspberry-5MP-Camera-Board-Module/dp/B00E1GGE40/ref=wl_it_dp_o_pd_S_nC?ie=UTF8&colid=3AHXZEFR7P8ZM&coliid=I2D9TFB0V615PM | 2014-01-06 | Acquired
Ground:TelStation
… | Laptop | N/A | 1 | N/A |  | N/A | N/A | Acquired
Quad:PCB_HW
… | Microcontroller Standalone |  | 2 |  |  |  | 2014-02-03 | Acquired
… | Accelerometer |  | 2 |  |  |  | 2014-02-03 | Acquired
… | Gyroscope |  | 2 |  |  |  | 2014-02-03 | Acquired
… | Magnetometer |  | 2 |  |  |  | 2014-02-03 | Acquired
… | Altimeter |  | 2 |  |  |  | 2014-02-03 | Acquired
TOTALS | All |  |  |  | 671.22 |  | N/A | N/A

## Team Organization
Team Member Name | Job Title | Job Description
Nathaniel Cain, EE | Team Lead, Control Sys Lead | Team Lead, Control Systems, Avionics, DTN Lead, NASA liason
James Donegan, EE | Hardware Lead, Power Lead | Power Distribution, Hardware Layout, Integration, Document Tracking
James Gregory, EE | PCB Lead, Hardware Backup | PCB design, Wiring, Control Backup
Wade Henderson, CpE | Software Lead, Team Lead Backup | Software org, Firmare, RTOS Implementation, Ground Station GUI

## Status
ITEM | Nate | Wade | Donnegan | Gregory | Need-By | STATUS
Parts Acquisition | x | x | x | x | N/A | DONE
TIVA C (Flight Computer)
RTOS, Sensor Drivers | x | x |  |  |  | DONE
Motor Control, Reciever Input | x | x |  |  |  | DONE
Control System(Roll/Pitch, Yaw) | x | x | x | x |  | ALMOST
GPS Drivers, Altimeter, A/D Code |  | x |  |  |  | DONE
RASPBERRY PI (Navigation Computer)
UART, Parsing |  |  | x | x |  | DONE
Pi Cam | x | x |  |  |  | DONE
Telemetry Software | x | x | x | x |  | ALMOST
Navigation, Autonomous | x | x | x | x |  | N/A
PCB
Circuit Design | x | x | x | x |  | DONE
Routing, Layout |  |  |  | x |  | DONE
Order, Populate |  |  |  | x |  | DONE
Testing | x |  | x | x |  | DONE
Mounting | x | x | x | x |  | DONE
GROUND STATION
GUI, Ground Station Software, Control |  | x |  |  |  | ALMOST
DTN, P2P Wireless Network | x | x |  |  |  | DONE
Linux Interfacing | x | x |  |  |  | DONE
Image Stitching |  | x |  |  |  | DONE
DOCUMENTATION
Fix PDR |  |  | x |  | 2014-03-28 | DONE
Conference Paper |  |  | x |  | 2014-04-04 | DONE
Committee Formation |  |  | x |  |  | DONE
Final Presentation | x | x | x | x | 2014-04-16 | ALMOST
TEST DATA | x | x | x | x | 2014-04-16 | ALMOST
Final Paper/Website | x | x | x | x | 2014-04-28 | NOT STARTED

## Budget&Parts-Generic
Category | Item | QTY | Price Ea. ($) | Total $ | Need By Date | Status
Quad:ControlSys
… | Microcontroller Launchpad | 2 | 15 | 30 | 2013-09-30 | Acquired
… | IMU Sensor Unit | 2 | 25 | 50 | 2013-09-30 | Acquired
… | GPS Unit | 2 | 50 | 100 | 2013-09-30 | Acquired
Quad:FlightSys
… | Speed Controller | 8 | 10 | 80 | 2013-11-04 | Acquired
… | Motors | 8 | 20 | 160 | 2013-11-04 | Acquired
… | Props | 12 | 4 | 48 | 2013-11-04 | Acquired
… | Frame | 2 | 15 | 30 | 2013-11-04 | Acquired
… | Li-Po Battery (4-5 A-h) | 2 | 40 | 80 | 2013-11-04 | Acquired
… | RC Controller & Reciever | 1 | 50 | 50 | 2013-11-04 | Acquired
Quad:GuidSys
… | Embedded Linux Processor | 2 | N/A |  | N/A | Acquired
… | Power Cable | 2 | N/A |  | N/A | Acquired
… | SD Cards | 2 | N/A |  | N/A | Acquired
… | 802.11G Wireless Card | 2 | N/A |  | N/A | Acquired
… | High Resolution Webcam | 2 | 50 | 100 | 2014-01-06 | Acquired
Ground:GndStat
… | Laptop | 1 | N/A |  | N/A | Acquired
Quad:PCBHardW
… | Microcontroller Standalone | 2 | Free | Free | 2014-02-03 | Acquired
… | Accelerometer | 2 | Free | Free | 2014-02-03 | Acquired
… | Gyroscope | 2 | 5 | 10 | 2014-02-03 | Acquired
… | Magnetometer | 2 | 5 | 10 | 2014-02-03 | Acquired
… | Altimeter | 2 | 5 | 10 | 2014-02-03 | Acquired
… | Passive Components |  | Free |  | N/A | Acquired
… | Active Components |  | Free |  | N/A | Acquired
TOTALS | All |  |  | 758 | N/A | N/A

## Flight Time-Calculator
Part | Description | Part # | Mass (g) | Qty | Current (A) | Thrust (g) | Capacity (Ah)
Frame | Fiber Glass Quadcopter Frame (450mm) | Q450 | 280 | 1 | 0 | 0 | 0
Propeller Motors | Prop Drive 900KV/270W Motor | NTM2830S-900 | 66 | 4 | 10.6 | 750 | 0
Electronic Speed Controller | Afro 20Amp ESC | 919200131-0 | 23 | 4 | 0 | 0 | 0
Battery | Turnigy 4s Lipo Battery | N5000.4S.45 | 552 | 1 | 0 | 0 | 5
Propeller | 8x4.5 Propellers | 17000055 | 15 | 4 | 0 | 0 | 0
Avionics | Controls, Processors, Sensors etc. | Tiva/Raspi | 200 | 1 | 1 | 0 | 0
| TOTALS | N/A | 1448 |  | 43.4 | 3000 | 5
%Throttle to Keep Static in Air | 0.48267 | [7 empty] | Prop Drive 800KV/300W Motor | Prop Drive 900KV/270W Motor | Prop Drive 1000KV/235W Motor
Current Drain (A) | 21.4651 | [6 empty] | %Throttle to Keep Static in Air | 0.34381 | 0.48267 | 0.37353
Flight Time (Minutes) | 13.9762 | [6 empty] | Current Drain (A) | 25.4792 | 21.4651 | 23.2625
[8 empty] | Flight Time (Minutes) | 11.7743 | 13.9762 | 12.8963
Part | Description | Part # | Mass (g) | Qty | Current (A) | Thrust (g) | Capacity (Ah)
Frame | Fiber Glass Quadcopter Frame (450mm) | Q450 | 280 | 1 | 0 | 0 | 0
Propeller Motors | Prop Drive 800KV/300W Motor | NTM2830S-900 | 65 | 4 | 17.8 | 1050 | 0
Electronic Speed Controller | Afro 20Amp ESC | 919200131-0 | 23 | 4 | 0 | 0 | 0
Battery | Turnigy 4s Lipo Battery | N5000.4S.45 | 552 | 1 | 0 | 0 | 5
Propeller | 8x4.5 Propellers | 17000055 | 15 | 4 | 0 | 0 | 0
Avionics | Controls, Processors, Sensors etc. | Tiva/Raspi | 200 | 1 | 1 | 0 | 0
| TOTALS | N/A | 1444 |  | 72.2 | 4200 | 5
%Throttle to Keep Static in Air | 0.34381
Current Drain (A) | 25.4792
Flight Time (Minutes) | 11.7743
Part | Description | Part # | Mass (g) | Qty | Current (A) | Thrust (g) | Capacity (Ah)
Frame | Fiber Glass Quadcopter Frame (450mm) | Q450 | 280 | 1 | 0 | 0 | 0
Propeller Motors | Prop Drive 1000KV/235W Motor | NTM2830S-900 | 54 | 4 | 14.9 | 937 | 0
Electronic Speed Controller | Afro 20Amp ESC | 919200131-0 | 23 | 4 | 0 | 0 | 0
Battery | Turnigy 4s Lipo Battery | N5000.4S.45 | 552 | 1 | 0 | 0 | 5
Propeller | 8x4.5 Propellers | 17000055 | 15 | 4 | 0 | 0 | 0
Avionics | Controls, Processors, Sensors etc. | Tiva/Raspi | 200 | 1 | 1 | 0 | 0
| TOTALS | N/A | 1400 |  | 60.6 | 3748 | 5
%Throttle to Keep Static in Air | 0.37353
Current Drain (A) | 23.2625
Flight Time (Minutes) | 12.8963

## Comparison of MCUs
Name | Vendor | Processor | RTOS Support | Availiability | Price
UNO32 | Digilent | PIC32MX320F128 | No | Launchpad, Standalone | 26.95
Piccolo Launchpad | Texas Instruments | F28027F | Yes | Launchpad, Standalone | 17
Stellaris Launchpad | Texas Instruments | EK-LMF120XL | Yes | Launchpad only | 13.49
Tiva C Launchpad | Texas Instruments | TM4C123GH6PMI | Yes | Launchpad, Standalone | 12.99